## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 03.01.2026. | Almedin Džinić | 1. Open Google Chrome web brower 2. Go to www.giga.ba 3. Click on the person icon 4. Click on the "Napravi račun" 5. Click the "Ime" field and type in "TestFirstName" 6. Click the "Prezime" field and type in "TestLastName" 7. Click the "E-mail" field and type in any valid email address (the system only allows one account per email address) 8. Click the "Lozinka" field and type in "test123" 9. Click "Napravi račun" button 10. Click on the person icon 11. Click on the "Adresna knjiga" 12. Scroll down and press the "Uredi" button 13. Click on the "Ime" field and change "TestFirstName" to "FirstNameChanged" 14. Click on the "Prezime" field and change "TestLastName" to "LastNameChanged" 15. Click on the button "Ažuriraj" 16. Click again on the person icon and verify that the first name and the last name did not change (it is still the first name and the last name the user used for registartion) EXPECTED RESULT: The system updates the first name and last name with the newly provided information SCREENSHOTS: - https://prnt.sc/2vlRiTxDhrrc | [6 empty] | New |  |  |  |  | New
2 | 03.01.2026. | Almedin Džinić | 1. Open Google Chrome web brower 2. Go to www.giga.ba 3. Click on the search and search up "Intel i3" 4. Click on the "Procesor za CPU Intel Core i3 12100F 3.3 GHz" 5. Click on the "Dodaj u košaricu" button (leave the option 5-9 quantity selected) 6. Click on the cart icon 7. Verify that there is an item in the cart but the user is not able to proceed to the payment screen (The cart is still recognized as empty) EXPECTED RESULT: The item is added to the cart and the user can proceed to the payment screen SCREENSHOTS: - https://prnt.sc/F8p2ImRbtb5- | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 03.01.2026. | Almedin Džinić | 1. Open Google Chrome web brower 2. Go to www.giga.ba 3. Click on the person icon 4. Click on the "Prijava" button 5. Click on the "E-mail" field and type in mujomujic321@yahoo.com 6. Click on the "Lozinka" field and type in test123 7. Click on the "Prijavi se" button 8. Scroll down to the "You May be Interested" section 9. Verify that only the placeholder text is displayed not some items EXPECTED RESULT: Display the most popular items even though the user doesn't have purchase history SCREENSHOTS: - https://prnt.sc/UR4hlbX2jsZ7 | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 04.01.2026. | Almedin Džinić | 1. Open Google Chrome web brower 2. Go to www.giga.ba 3. Click on the search and search up "YT 9050" 4. Click on the "FLEXI KANCELARIJSKA RADNA UREDSKA STOLICA YT-9050 CRNA" 5. Click on the "Dodaj u košaricu" button 6. Change the quantity from 5 to 900 7. Verify that there are two different quantity values displayed for the item in the cart, which could leave the user uncertain EXPECTED RESULT: The quantity of the cart matches the quantity of the item SCREENSHOT: - https://prnt.sc/2G0WmCb5JTJW | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 04.01.2026. | Almedin Džinić | 1. Open Google Chrome web brower 2. Go to www.giga.ba 3. Click on the search and search up "YT 9050" 4. Click on the "FLEXI KANCELARIJSKA RADNA UREDSKA STOLICA YT-9050 CRNA" 5. Click on the "Dodaj u košaricu" button 6. Click on the "Idi u košaricu" 7. Change the quantity from 5 to 11 8. Change the quantity from 11 to 500 9. Verify that the displayed quantity is returned to the last valid quantity even though the user is notified that 180 items were added to the cart; the price is not updated to match the 180 added items EXPECTED RESULT: The quantity is adjusted to the maximum available stock, and the price is calculated based on that quantity. SCREENSHOT: -https://prnt.sc/1uf6kVH5kwsz | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | [16 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.

## Defect Tracking Log Instruc
Defect Tracking Log Instructions
Field | Description
Defect Number | Unique identifier for the defect, i.e., 1,2 etc.
Date Created | Date on which the defect was initially reported and logged.
Created By | Name of the person who reported the defect.
Defect Description | Description of the defect. State the subsystem, area, or other part of the product in which the defect occurs or which is affected by the defect.
PM Process | Choose the Project Management Process this defect was reported for: Opportunity Assessment, Initiating, Planning, Executing/Controlling and Closing.
Lifecycle Phase | List the lifecycle this defect was reported for. The Software Development lifecycle is: Opportunity Assessment, Concept, Requirements, Design, Development, Testing, Documentation and Training, Deployment and Post Deployment.
Priority | The priority code indicates the impact of this defect on the project:
H = High (extremely important, the project cannot be successful without this defect being resolved)
M = Medium (important to project success, but a work around exists)
L = Low (desirable, but with little impact to project success if the defect is not resolved)
Owner | Name of the person who is responsible for fixing the defect.
Assigned Date | Date on which the defect was assigned for resolution.
Estimated Time To Fix | Estimated amount of time required to correct the defect. If applicable list in hours, not days.
Status | Current status of the defect: New, In Progress, Under Review and Completed.
Resolution | Description of the defect’s resolution.
Resolution Date | Date on which the defect is to be resolved (or is resolved depending upon its status).
Actual Time to Fix | Actual time required to correct the defect.
Root Cause Description | State the cause of the defect (for example, communication, oversight, transcription, education, process, bad code.).